## Sheet1
Project Plan
Description : Create a CNN model to classify images as cancerous vs non cancerous
Date : August 18, 2025 - December 12, 2025
Owner : Devanshu Arora
Status : Final
Task | Description | Owner | Timeline
Team Formation | Pairing up with classmate to form team |  | Week 1
Ideas Brainstorming | Gathering ideas for project | Devanshu | Week 2
Project Preposal | Providing overview of project | Devanshu | Week 3
Dataset Preparation | Collect & preprocess microscopic images | Devanshu | Week 4 - 5
Model Development | Build transfer-learning model(ResNet) | Devanshu | Week 6 - 9
Training & Tuning | Train and hyper-tune model | Devanshu | Week 10 - 11
Evaluation | Compute metrics, confusion matrix | Devanshu | Week 11 - 14
Documentation | Write project report | Devanshu | Week 15
Presentation | Prepare and deliver presentation | Devanshu | Week 16